## Team
Initials | First | Last | Email | GitHub Username
py | PoYu | Yang | corupted5354.cv99@g2.nctu.edu.tw | dar1enyang
cs | Chieh | Shih | nowiznesh4113@hotmail.com | leehon3322
mh | Ming-Ting | Hsieh | cosoet@gmail.com | cosoet
shh | Shih-Hsuan | Huang | jasonh6208@yahoo.com.tw | jasonh6208
GitHub Link
https://github.com/SSW-555-Project/projectRepo

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | py | coding
1 | US02 | Birth before marriage | cs | coding
1 | US03 | Birth before death | mh | coding
1 | US04 | Marriage before divorce | shh | coding
1 | US05 | Marriage before death | mh | coding
1 | US06 | Divorce before death | py | coding
1 | US07 | Less then 150 years old | cs | coding
1 | US08 | Birth before marriage of parents | shh | coding
| US09 | Birth before death of parents
| US10 | Marriage after 14
| US11 | No bigamy
| US12 | Parents not too old
| US13 | Siblings spacing
| US14 | Multiple births <= 5
| US15 | Fewer than 15 siblings
| US16 | Male last names
| US17 | No marriages to descendants
| US18 | Siblings should not marry
| US19 | First cousins should not marry
| US20 | Aunts and uncles
| US21 | Correct gender for role
| US22 | Unique IDs
| US23 | Unique name and birth date
| US24 | Unique families by spouses
| US25 | Unique first names in families
| US26 | Corresponding entries
| US33 | List orphans
| US28 | Order siblings by age
| US29 | List deceased
| US30 | List living married
| US31 | List living single
| US32 | List multiple births

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | py | coding | 70 | 120
US02 | Birth before marriage | cs | coding | 115 | 130
US03 | Birth before death | mh | coding | 50 | 155
US04 | Marriage before divorce | shh | coding | 90 | 150
US05 | Marriage before death | mh | coding | 50 | 155
US06 | Divorce before death | py | coding | 100 | 120
US07 | Less then 150 years old | cs | coding | 120 | 180
US08 | Birth before marriage of parents | shh | coding | 80 | 100